## Gantt Chart
GANTT CHART P6-8
PROJECT TITLE |  | Train Services Management |  |  |  |  | COMPANY NAME | [6 empty] | Train Co.
PROJECT MANAGER |  | Law Jun Hao |  |  |  |  | DATE | [6 empty] | 2023-09-20
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION (Days) | PCT OF TASK COMPLETE | M1 | [19 empty] | M2 | [19 empty] | M3
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Scope | ALL | 2022-09-10 | 2022-09-10 | 2 | 100% | bar: WEEK 1 F to WEEK 2 M
1.1.1 | Requirement Analysis | ALL | 2022-09-11 | 2022-09-11 | 4 | 100% | bar: WEEK 1 F to WEEK 2 W
1.2 | Use Case Model | ALL | 2022-09-12 | 2022-09-12 | 7 | 100% | bar: WEEK 2 W to WEEK 3 R
1.2 | Setting up of Github Repos/Wiki and Project Board | ALL | 2022-09-12 | 2022-09-12 | 7 | 100% | bar: WEEK 2 W to WEEK 3 R
1.3 | Use Case Description | ALL | 2022-09-13 | 2022-09-13 | 6 | 100% | bar: WEEK 2 R to WEEK 3 R
1.4 | Review of Use Case | ALL | 2022-09-14 | 2022-09-14 | 4 | 100% | bar: WEEK 3 M to WEEK 3 R
1.5 | Requirement Elicitations (Client Meeting) | ALL | 2022-09-15 | 2022-09-15 | 1 | 100% | bar: WEEK 3 R
1.6 | Requirement Documentation | ALL | 2022-09-16 | 2022-09-16 | 1 | 100% | bar: WEEK 3 F
2 | Analysis Phase
2.1 | Functional requirements | ALL | 2022-09-15 | 2022-09-18 | 4 | 100% | bar: WEEK 3 R to WEEK 4 T
2.2 | Non-Functional Requirements | ALL | 2022-09-16 | 2022-09-18 | 3 | 100% | bar: WEEK 3 F to WEEK 4 T
2.3 | Performance Requirements | ALL | 2022-09-17 | 2022-09-19 | 3 | 100% | bar: WEEK 4 M to WEEK 4 W
2.4 | Safety and Security Requirements | ALL | 2022-09-17 | 2022-09-19 | 3 | 100% | bar: WEEK 4 M to WEEK 4 W
2.5 | Other Requirements | ALL | 2022-09-18 | 2022-09-21 | 4 | 100% | bar: WEEK 4 T to WEEK 4 F
3 | Design Phase
3.1 | Architecture Design | Junhao, Edwin |  |  | 5 | 100% | bar: WEEK 4 R to WEEK 5 W
3.2 | Detailed Design (Wireframe) | ALL |  |  | 4 | 50% | bar: WEEK 5 W to WEEK 6 M
3.2.1 | Sequence Design | ALL |  |  | 5 | 50% | bar: WEEK 5 F to WEEK 6 R
3.2.2 | Design Review | Jun Hao, Yu Xiang |  |  | 3 | 0% | bar: WEEK 6 W to WEEK 6 F
4 | Implementation Phase
4.1 | Development of Front Page (Login Etc) | Edwin, Jun Hao |  |  | 9 | 0% | bar: WEEK 5 W to WEEK 7 M
4.11 | Development of Landing Page | Zi Ping |  |  | 5 | 0% | bar: WEEK 5 W to WEEK 6 T
4.12 | Development of 2FA for login | Zi Ping |  |  | 2 | 0% | bar: WEEK 6 T to WEEK 6 W
4.13 | Review of Front and Landing Page with client | Jun Hao, Zi Ping, Yu Xiang, Edwin |  |  | 1 | 0% | bar: WEEK 7 T
4.21 | Development of Rejection Page (Manager) | Zi Ping |  |  | 4 | 0% | bar: WEEK 6 W to WEEK 7 M
4.22 | Development of Job allocation Page (Manager) | Zi Ping |  |  | 3 | 0% | bar: WEEK 7 M to WEEK 7 W
4.23 | Development of Profile Page Staff | Zi Ping |  |  | 3 | 0% | bar: WEEK 7 R to WEEK 8 M
4.24 | Development of Profile Page Manager | Zi Ping |  |  | 3 | 0% | bar: WEEK 8 T to WEEK 8 R
4.3 | Development of SQL database to store user information | Edwin, Yu Xiang |  |  | 3 | 0% | bar: WEEK 7 T to WEEK 7 W
4.4 | Review of SQL database with client | Edwin, Yu Xiang |  |  | 6 | 0% | bar: WEEK 7 F to WEEK 8 F
4.5 | Reivew of Profile Pages, Job Allocation as well as Rejection Page | Edwin, Jun Hao, Yu Xiang |  |  | 3 | 0% | bar: WEEK 8 W to WEEK 8 F
4.6 | Documentation of implementation | ALL |  |  | 20 | 0% | bar: WEEK 5 M to WEEK 8 F
5 | Testing Phase
5.1 | Black Box Testing | Edwin, Yu Xiang |  |  | 4 | 0% | bar: WEEK 9 M to WEEK 9 R
5.2 | White Box Testing | Edwin, Yu Xiang |  |  | 4 | 0% | bar: WEEK 9 M to WEEK 9 R
5.3 | System Corrections | Edwin, Yu Xiang |  |  | 4 | 0% | bar: WEEK 9 F to WEEK 10 W
5.4 | Testing Documentation | Edwin, Yu Xiang |  |  | 4 | 0% | bar: WEEK 9 F to WEEK 10 W
6 | Maintenance Phase
6.1 | Software add-ons (Upon Client Request) | Edwin, Yu Xiang |  |  | 4 | 0% | bar: WEEK 10 R to WEEK 11 T
6.2 | Software Maintainence | Edwin, Yu Xiang |  |  | 4 | 0% | bar: WEEK 11 M to WEEK 11 R
6.3 | Debugging | Edwin, Yu Xiang |  |  | 4 | 0% | bar: WEEK 11 W to WEEK 12 M
6.4 | Documentation of additional add-ons | Edwin, Yu Xiang |  |  | 4 | 0% | bar: WEEK 11 F to WEEK 12 W
6.5 | Review of add-ons | ALL |  |  | 4 | 0% | bar: WEEK 12 T to WEEK 12 F