## Gantt Chart
GANTT CHART P6-8
PROJECT TITLE |  | Train Services Management |  |  |  |  | COMPANY NAME | [6 empty] | Train Co.
PROJECT MANAGER |  | Law Jun Hao |  |  |  |  | DATE | [6 empty] | 2023-09-20
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION (Days) | PCT OF TASK COMPLETE | M1 | [19 empty] | M2 | [19 empty] | M3
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Scope | ALL | 2022-09-09 | 2022-09-12 | 2 | 100% | bar: WEEK 1 F to WEEK 2 M
1.1.1 | Requirement Analysis | ALL | 2022-09-09 | 2022-09-14 | 4 | 100% | bar: WEEK 1 F to WEEK 2 W
1.2 | Use Case Model | ALL | 2022-09-14 | 2022-09-22 | 7 | 100% | bar: WEEK 2 W to WEEK 3 R
1.2 | Setting up of Github Repos/Wiki and Project Board | ALL | 2022-09-14 | 2022-09-22 | 7 | 100% | bar: WEEK 2 W to WEEK 3 R
1.3 | Use Case Description | ALL | 2022-09-16 | 2022-09-22 | 6 | 100% | bar: WEEK 2 R to WEEK 3 R
1.4 | Review of Use Case | ALL | 2022-09-18 | 2022-09-22 | 4 | 100% | bar: WEEK 3 M to WEEK 3 R
1.5 | Requirement Elicitations (Client Meeting) | ALL | 2022-09-22 | 2022-09-22 | 1 | 100% | bar: WEEK 3 R
1.6 | Requirement Documentation | ALL | 2022-09-23 | 2022-09-23 | 1 | 100% | bar: WEEK 3 F
2 | Analysis Phase
2.1 | Functional requirements | ALL | 2022-09-15 | 2022-09-18 | 4 | 100% | bar: WEEK 3 R to WEEK 4 T
2.2 | Non-Functional Requirements | ALL | 2022-09-16 | 2022-09-18 | 3 | 100% | bar: WEEK 3 F to WEEK 4 T
2.3 | Performance Requirements | ALL | 2022-09-17 | 2022-09-19 | 3 | 100% | bar: WEEK 4 M to WEEK 4 W
2.4 | Safety and Security Requirements | ALL | 2022-09-17 | 2022-09-19 | 3 | 100% | bar: WEEK 4 M to WEEK 4 W
2.5 | Other Requirements | ALL | 2022-09-18 | 2022-09-21 | 4 | 100% | bar: WEEK 4 T to WEEK 4 F
3 | Design Phase
3.1 | Architecture Design | Junhao, Edwin | 20/09/22 | 24/09/22 | 5 | 100% | bar: WEEK 4 R to WEEK 5 W
3.2 | Detailed Design (Wireframe) | ALL | 24/09/22 | 27/09/22 | 4 | 50% | bar: WEEK 5 W to WEEK 6 M
3.2.1 | Sequence Design | ALL | 30/09/22 | 2022-10-06 | 7 | 50% | bar: WEEK 5 F to WEEK 6 R
3.2.2 | Design Review | Jun Hao, Yu Xiang | 2022-10-05 | 2022-10-07 | 3 | 0% | bar: WEEK 6 W to WEEK 6 F
4 | Implementation Phase
4.1 | Development of Pages | Edwin, Jun Hao | 2022-09-28 | 2022-10-12 | 15 | 0% | bar: WEEK 5 W to WEEK 7 W
4.1.1 | Front Page (Login Etc) | Zi Ping | 2022-09-28 | 30/09.22 | 5 | 0% | bar: WEEK 5 W to WEEK 5 F
4.1.2 | Landing Page (Staff/Manager/Admin) | Zi Ping | 2022-10-03 | 2022-10-05 | 2 | 0% | bar: WEEK 6 M to WEEK 6 W
4.1.3 | 2FA for Authentication | Jun Hao, Zi Ping, Yu Xiang, Edwin | 2022-09-29 | 2022-10-04 | 6 | 0% | bar: WEEK 5 R to WEEK 6 T
4.1.4 | Reject Page (Manager/Admin) | Zi Ping | 2022-10-06 | 2022-10-10 | 5 | 0% | bar: WEEK 6 R to WEEK 7 M
4.1.5 | Profile Page (Staff/Manager/Admin) | Zi Ping | 2022-10-11 | 2022-10-12 | 2 | 0% | bar: WEEK 7 T to WEEK 7 W
4.1.6 | Account Creation Page (Admin) | Zi Ping | 13/10/22 | 17/10/22 | 5 | 0% | bar: WEEK 7 R to WEEK 8 M
4.1.7 | Job Preference Page (Staff) | Zi Ping | 2022-10-18 | 2022-10-21 | 4 | 0% | bar: WEEK 8 T to WEEK 8 F
4.1.9 | Staff Listing Page (Under Assigned/Over 40 hours) | Edwin, Yu Xiang | 2022-10-11 | 2022-10-12 | 2 | 0% | bar: WEEK 7 T to WEEK 7 W
4.2 | Review of Pages Developed | Edwin, Yu Xiang | 2022-10-05 | 21/10/22 | 16 | 0% | bar: WEEK 6 W to WEEK 8 F
4.2.1 | Front Page, Landing Page and 2FA | Edwin, Jun Hao, Yu Xiang | 2022-10-19 | 21/10/23 | 3 | 0% | bar: WEEK 8 W to WEEK 8 F
4.2.2 | Reject Page, Profile Page, Job Preference Page | Zi Ping, Edwin, Jun Hao | 2022-10-05 | 2022-10-13 | 8 | 0% | bar: WEEK 7 T to WEEK 8 W
4.2.3 | Staff Listing Page (Under Assigned/Over 40 hours) | Zi Ping, Jun Hao | 2022-10-20 | 2022-10-21 | 2 | 0% | bar: WEEK 8 R to WEEK 8 F
4.3 | Implementation of SQL database to store user information | Edwin | 2022-09-28 | 2022-10-21 | 23 | 0% | bar: WEEK 5 W to WEEK 8 F
4.3.1 | Review of SQL database with client | ALL | 2022-09-28 | 2022-10-21 | 23 | 0% | bar: WEEK 5 W to WEEK 8 F
5 | Testing Phase
5.1 | Black Box Testing | Edwin, Yu Xiang | 2022-10-24 | 2022-10-27 | 4 | 0% | bar: WEEK 9 M to WEEK 9 R
5.2 | White Box Testing | Edwin, Yu Xiang | 2022-10-24 | 2022-10-27 | 4 | 0% | bar: WEEK 9 M to WEEK 9 R
5.3 | System Corrections | Edwin, Yu Xiang | 2022-10-28 | 2022-11-02 | 4 | 0% | bar: WEEK 9 F to WEEK 10 W
5.4 | Testing Documentation | Edwin, Yu Xiang | 2022-10-28 | 2022-11-02 | 4 | 0% | bar: WEEK 9 F to WEEK 10 W
6 | Maintenance Phase
6.1 | Software add-ons (Upon Client Request) | Edwin, Yu Xiang | 2022-11-03 | 2022-11-08 | 4 | 0% | bar: WEEK 10 R to WEEK 11 T
6.2 | Software Maintainence | Edwin, Yu Xiang, Zi Ping, Jun Hao | 2022-11-07 | 2022-11-10 | 4 | 0% | bar: WEEK 11 M to WEEK 11 R
6.3 | Debugging | Edwin, Yu Xiang | 2022-11-09 | 2022-11-14 | 4 | 0% | bar: WEEK 11 W to WEEK 12 M
6.4 | Documentation of additional add-ons | Edwin, Yu Xiang, Zi Ping, Jun Hao | 2022-11-11 | 2022-11-16 | 4 | 0% | bar: WEEK 11 F to WEEK 12 W
6.5 | Review of add-ons | ALL | 2022-11-15 | 2022-11-18 | 4 | 0% | bar: WEEK 12 T to WEEK 12 F